

**WINCHESTER COMMUNITY SAFETY PARTNERSHIP**

**ANNUAL DELIVERY PLAN 2020-21**

|  |
| --- |
| **PRIORITY ONE: Domestic violence and abuse** |
| **Objective** | **Measure** | **Lead Agency** | **Target Date** | **Expected Outcome** |
| **Objective 1:**To increase the number of Formal Action Taken (FAT) outcomes. | * Arrest and positive disposal rates provided on a quarterly basis.
* Data updates put into context.
 | Hampshire Constabulary | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020-Mar 2021
 | * Trends and opportunities for reducing the number of repeat victims identified.
* Contextual information used to ‘share the story’.[[1]](#footnote-2)
 |
| * Police enforcement and intervention in place aimed at reducing the number of repeat offenders e.g. target hardening, targeted action and intervention.
 | Hampshire Constabulary | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020-Mar 2021
 | High risk cases flagged for targeted action/intervention via the Police Tactical Meeting.  |
| **Objective 2:** To reduce the total number of repeat domestic abuse victims and offenders. | Minimise the risk of repeat offending by increasing the use of bail conditions and disruption tactics:* Domestic Violence Protection Notices/Domestic Violence Protection Orders,
* Non molestation orders,
* Clares Law,
* Injunctions,
* MARAC,
* High Risk Domestic Abuse (HRDA) meetings for domestic abuse,
* DASH risk assessment, IDVA, IDAP (interventions and support services).
 | Hampshire Constabulary/STOP Domestic Abuse/RSLs, Criminal Justice Services, support services. | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020- Mar 2021
 | * Number of bail conditions and disruption tactics increased for the most prolific perpetrators.
* Number of victims of violence and abuse supported through the criminal justice process.
* Use of tools and powers in place which aids support to both victims and those at risk of being a victim or perpetrator.
 |
| * Scoping exercise undertaken with domestic abuse support services around the impact of Covid-19 on victims and offenders.
 | STOP Domestic Abuse | 31st March 2021 | Scoping outcomes reviewed and any partnership action in place. |
| * Ensure support is in place to maximise evidential opportunities.
 | Hampshire Constabulary/STOP Domestic Abuse/RSLs, Criminal Justice Services, support services. | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020- Mar 2021
 | Improved evidence collection. |
| **Objective 3:** Ensure delivery of recommendations arising from the serious case review, monitoring progress via an annual review.  | * DHR package will be implemented for serious case review.
* Review the outcomes/recommendations as reported to the CSP via serious case review.
* Grant funding applications reviewed and advice/support discussed.
 | WCC Community Safety Team/CSP Chair | 31st March 2021 | * Commissioned process in place.
* Action plan developed and managed by the CSP.
* Applications supported and local delivery implemented.
* Grant funding specially related to domestic violence/abuse support reviewed and advice/support offered.
 |

|  |
| --- |
| **PRIORITY TWO: Drug Related Harm** |
| **Objective** | **Measure** | **Lead Agency** | **Target Date** | **Expected Outcome** |
| **Objective 1:** Reduce the number of hotspot locations. | The most serious violent crimes to include drug related violence will be tackled:* County lines activity
* Robbery
* Street crime
* Residential burglary
* Cuckooing
 | Hampshire Constabulary in partnership with multi agencies.  | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020-Mar 2021
 | * Reduction in hot spot locations.
* Number of operations/prosecutions achieved via Operation Fortress.
* Support in place for those most vulnerable e.g. increased referrals to housing and support services.
 |
| **Objective 2:** To increase the number of Formal Action Taken (FAT) outcomes by utilising a range of disposal options, including out of court disposals when appropriate. | Arrest and positive disposal rates (See priority two: objective 1)  | Hampshire Constabulary | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020-Mar 2021
 | * Reduction in substantive crime being committed.
* Increased public confidence.
* Increased use of out of court disposals.
 |
| **Objective 3:**To reduce drug related violence incidents**.** | * County VRUs in place via the 4 pilot areas.
* Multi-agency work streams in place and CSP support identified.
 | Director of Public Health (OPCCCounty CS Strategy Group) | 31st March 2021 | * Pan Hampshire and IOW collaboration in place e.g. Winchester CSP support to the 7 work streams.
* Problem profile and response plan in place for 2020/21.
 |

|  |
| --- |
| **PRIORITY THREE: Quality of Life** |
| **Objective 1:**Reduce the number of ASB victims and repeat offenders.  | Collaborative arrangements in place between businesses and external partners to address the following issues:* Begging
* Street drinking
* Local drug dealing/usage
* Illegal encampments/squatting
 | WCC Services in conjunction with external partners e.g. Police and BID | 31st March 2021 | * Reduction in the number of calls for service.
* Increase in public confidence in reporting crime and disorder issues.
* Delivery of the Public Space Protection Order.
* ASB Satisfaction survey undertaken.
* Report provided for Council Scrutiny
 |
| ASB/Neighbourhoods:* Remedial action and diversionary activity identified
* ASB legislative tools and powers used
* Collaborative arrangements in place via, operational level agreements with Registered Social Landlords (RSLs).
 | Neighbourhood Services Officer - ASB | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020-Mar 2021
 | * Increase in public confidence in reporting crime and disorder issues.
* Projects and initiatives in place to improve the quality of life for those who live, work and visit the Winchester District.
* Remedial action and diversionary activity supported and implemented.
* Operational level agreements with RSLs in place.
 |
| **Objective 2:** Continue to take a zero tolerance approach to fly tipping incidents and increase the number of positive enforcement interventions  | * Year on year data used to identify hotspot locations.
* Data provided on the number of reported fly-tipping incidents and the related prosecutions or interventions (FPNs, CPWs, CPNs, and Prosecutions etc.)
* Data provided on the size (tonnage) of fly tips removed.
 | Neighbourhood Services Officer- Fly Tip Enforcement | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020- Mar 2021
 | * A reduction in fly tips in Hotspot Locations.
* 100% prosecution rate achieved for all court applications.
* Report provided for Council Scrutiny.
 |
| * Collaborative arrangements in place with private landowners in relation to fly tipping incidents on private land to facilitate prosecution/enforcement action being taken against offenders.
* Data provided on the number of fly tipping incidents investigated on private land and the related interventions and prosecutions.
 | Neighbourhood Services Officer- Fly Tip Enforcement | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020- Mar 2021
 | * Report provided for Council Scrutiny.
* Timely clearance of fly tip incidents on private land.
* A reduction in fly tips on private land.
* 100% prosecution rate achieved for all court applications.
 |
| **Objective 3:**Reduce the opportunity for those who target our most vulnerable.  | Reinvigorate the Anti-Social Behaviour Panel or equivalent to ensure that those coming to the attention of partner agencies are subject to partnership activity e.g. support, enforcement through the use of operational level agreements with relevant partners, in relation to the following issues:* Begging
* Street drinking
* Business crime e.g. shop lifting
 | WCC Services in conjunction with external partners e.g. Police and BID | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020- Mar 2021
 | * Accountability in place between businesses and external partners.
* Delivery of the Public Space Protection Order.
* Report provided for Council Scrutiny
 |
| Partnership enforcement and intervention in place e.g. target hardening, targeted action and intervention, collaboration with support services, in relation to the following:* + Exploitation
	+ Cuckooing
	+ Scams
 | WCC Services in conjunction with external partners e.g. Police and relevant support services | * June-Sept 2020
* Sept-Dec 2020
* Dec 2020-Mar 2021
 | * High risk offenders flagged for targeted action/intervention via the Police Tactical Meeting.
* ASB tools and powers used for persistent offenders
* Reduction in the number of calls for service
 |

1. Contextual information – used to validate the data being shared by lead partner. [↑](#footnote-ref-2)